## Defects modified today (hidden)
Defects modified Today | Column Labels
Row Labels | 3-Minor | Grand Total
Ready to test | 1 | 1 | id | Status | Severity | day | number of defect
Grand Total | 1 | 1 | 125 | New | Major | 2014-01-14 | 11
|  |  | 254 | Open | Critical | 2014-01-15 | 15
|  |  | 1 | Rejected | Minor | 2014-01-16 | 8 | Row Labels | Sum of number of defect
|  |  | 2 | New | Cosmetic | 2014-01-17 | 0 | 2014-01-14 | 11
|  |  | 3 | Open | Critical | 2014-01-18 | 0 | 2014-01-15 | 15
|  |  | 4 | Rejected | Major | 2014-01-19 | 15 | 2014-01-16 | 8
|  |  | 5 | Fixed | Minor | 2014-01-20 | 21 | 2014-01-17 | 0
|  |  | 6 | Ready to test | Major | 2014-01-21 | 4 | 2014-01-18 | 0
|  |  | 7 | Closed | Critical | 2014-01-22 | 34 | 2014-01-19 | 15
|  |  | 8 | New | Major |  |  | 2014-01-20 | 21
|  |  | 9 | Closed | Minor |  |  | 2014-01-21 | 4
|  |  | 10 | Open | Cosmetic |  |  | 2014-01-22 | 34
[8 empty] | Grand Total | 108

## Open by severity (hidden)
Open defects - Severity per period
Created on: 09.01.2014
Day | Status | Severity | count | Day | Status | Severity | count | Day | Status | Severity | count
2014-01-14 | New | Critical | 11 | 2014-01-14 | New | Critical | 11 | 2014-01-14 | Open | Critical | 12 | Sum of count | Column Labels
2014-01-14 | New | Major | 15 | 2014-01-14 | New | Major | 15 | 2014-01-14 | Open | Major | 2 | Row Labels | Cosmetic | Critical | Major | Minor | Grand Total
2014-01-14 | New | Minor | 0 | 2014-01-14 | New | Minor | 0 | 2014-01-14 | Open | Minor | 11 | 2014-01-14 | 18 | 12 | 2 | 11 | 43
2014-01-14 | New | Cosmetic | 1 | 2014-01-14 | New | Cosmetic | 1 | 2014-01-14 | Open | Cosmetic | 18 | 2014-01-15 | 24 | 12 | 5 | 2 | 43
2014-01-14 | Open | Critical | 12 | 2014-01-14 | Open | Critical | 12 | 2014-01-15 | Open | Critical | 12 | 2014-01-16 | 9 | 11 |  | 4 | 24
2014-01-14 | Open | Major | 0 | 2014-01-14 | Open | Major | 0 | 2014-01-15 | Open | Major | 5 | 2014-01-17 |  | 23 | 7 | 2 | 32
2014-01-14 | Open | Minor | 0 | 2014-01-14 | Open | Minor | 0 | 2014-01-15 | Open | Minor | 2 | Grand Total | 51 | 58 | 14 | 19 | 142
2014-01-14 | Open | Cosmetic | 18 | 2014-01-14 | Open | Cosmetic | 18 | 2014-01-15 | Open | Cosmetic | 24
2014-01-14 | Fixed | Critical | 4 | 2014-01-15 | New | Critical | 8 | 2014-01-16 | Open | Critical | 11
2014-01-14 | Fixed | Major | 0 | 2014-01-15 | New | Major | 4 | 2014-01-16 | Open | Major
2014-01-14 | Fixed | Minor | 1 | 2014-01-15 | New | Minor | 11 | 2014-01-16 | Open | Minor | 4
2014-01-14 | Fixed | Cosmetic | 13 | 2014-01-15 | New | Cosmetic | 0 | 2014-01-16 | Open | Cosmetic | 9
2014-01-14 | Ready to test | Critical | 1 | 2014-01-15 | Open | Critical | 12 | 2014-01-17 | Open | Critical | 23
2014-01-14 | Ready to test | Major | 2 | 2014-01-15 | Open | Major | 0 | 2014-01-17 | Open | Major | 7
2014-01-14 | Ready to test | Minor | 0 | 2014-01-15 | Open | Minor | 0 | 2014-01-17 | Open | Minor | 2
2014-01-14 | Ready to test | Cosmetic | 4 | 2014-01-15 | Open | Cosmetic | 18 | 2014-01-17 | Open | Cosmetic
2014-01-14 | Reopen | Critical | 3 | 2014-01-16 | New | Critical | 5
2014-01-14 | Reopen | Major | 1 | 2014-01-16 | New | Major | 7
2014-01-14 | Reopen | Minor | 12 | 2014-01-16 | New | Minor | 0
2014-01-14 | Reopen | Cosmetic | 0 | 2014-01-16 | New | Cosmetic | 24
2014-01-14 | Rejected | Critical | 0 | 2014-01-16 | Open | Critical | 11
2014-01-14 | Rejected | Major | 5 | 2014-01-16 | Open | Major | 0
2014-01-14 | Rejected | Minor | 7 | 2014-01-16 | Open | Minor | 4
2014-01-14 | Rejected | Cosmetic | 0 | 2014-01-16 | Open | Cosmetic | 9
2014-01-14 | Closed | Critical | 24 | 2014-01-17 | New | Critical | 13
2014-01-14 | Closed | Major | 11 | 2014-01-17 | New | Major | 18
2014-01-14 | Closed | Minor | 30 | 2014-01-17 | New | Minor | 41
2014-01-15 | New | Critical | 8 | 2014-01-17 | Open | Critical | 23
2014-01-15 | New | Major | 4 | 2014-01-17 | Open | Major | 7
2014-01-15 | New | Minor | 11 | 2014-01-17 | Open | Minor | 0
2014-01-15 | New | Cosmetic | 0 | 2014-01-17 | Open | Cosmetic | 0
2014-01-15 | Open | Critical | 12
2014-01-15 | Open | Major | 0
2014-01-15 | Open | Minor | 0
2014-01-15 | Open | Cosmetic | 18
2014-01-15 | Fixed | Critical | 4
2014-01-15 | Fixed | Major | 0
2014-01-15 | Fixed | Minor | 1
2014-01-15 | Fixed | Cosmetic | 13
2014-01-15 | Ready to test | Critical | 1
2014-01-15 | Ready to test | Major | 2
2014-01-15 | Ready to test | Minor | 0
2014-01-15 | Ready to test | Cosmetic | 15
2014-01-15 | Reopen | Critical | 0
2014-01-15 | Reopen | Major | 1
2014-01-15 | Reopen | Minor | 12
2014-01-15 | Reopen | Cosmetic | 0
2014-01-15 | Rejected | Critical | 0
2014-01-15 | Rejected | Major | 18
2014-01-15 | Rejected | Minor | 4
2014-01-15 | Rejected | Cosmetic | 0
2014-01-15 | Closed | Critical | 1
2014-01-15 | Closed | Minor | 0
[19 empty] | G0-Critical | G1-Major | G2-Minor | G3-Cosmetic |  | x_volar | x_pis
2014-01-15 | Closed | Cosmetic | 0 | [14 empty] | 2014-01-14 | 2 | 1 | 4 | 5 | 1
2014-01-16 | New | Critical | 5 | [14 empty] | 2014-01-15 | 2 | 2 | 1 | 1 | 2
2014-01-16 | New | Major | 7 | [14 empty] | 2014-01-16 | 3 | 3 | 2 | 2 | 3
2014-01-16 | New | Minor | 0 | [14 empty] | 2014-01-17 | 1 | 2 | 3 | 1 |  | 3 | 1
2014-01-16 | New | Cosmetic | 24 | [20 empty] | 1 | 4
2014-01-16 | Open | Critical | 11
2014-01-16 | Open | Major | 0
2014-01-16 | Open | Minor | 4
2014-01-16 | Open | Cosmetic | 9
2014-01-16 | Fixed | Critical | 1
2014-01-16 | Fixed | Major | 0
2014-01-16 | Fixed | Minor | 8
2014-01-16 | Ready to test | Major | 11
2014-01-16 | Ready to test | Minor | 0
2014-01-16 | Ready to test | Cosmetic | 7
2014-01-16 | Reopen | Critical | 2
2014-01-16 | Reopen | Cosmetic | 13
2014-01-16 | Rejected | Critical | 16
2014-01-16 | Rejected | Major | 11
2014-01-16 | Rejected | Minor | 8
2014-01-16 | Rejected | Cosmetic | 1
2014-01-16 | Closed | Critical | 40
2014-01-16 | Closed | Major | 13
2014-01-16 | Closed | Minor | 28
2014-01-16 | Closed | Cosmetic | 11
2014-01-17 | New | Critical | 13
2014-01-17 | New | Major | 18
2014-01-17 | Open | Critical | 23
2014-01-17 | Open | Major | 7
2014-01-17 | Open | Minor | 0
2014-01-17 | Open | Cosmetic | 0
2014-01-17 | Fixed | Critical | 14
2014-01-17 | Fixed | Major | 13
2014-01-17 | Fixed | Minor | 7
2014-01-17 | Fixed | Cosmetic | 4
2014-01-17 | Ready to test | Critical | 0
2014-01-17 | Ready to test | Major | 13
2014-01-17 | Ready to test | Minor | 14
2014-01-17 | Ready to test | Cosmetic | 17
2014-01-17 | Reopen | Critical | 0
2014-01-17 | Reopen | Major | 6
2014-01-17 | Reopen | Minor | 8
2014-01-17 | Reopen | Cosmetic | 13
2014-01-17 | Rejected | Minor | 7
2014-01-17 | Rejected | Cosmetic | 3
2014-01-17 | Closed | Critical | 24
2014-01-17 | Closed | Major | 27
2014-01-17 | Closed | Minor | 36
2014-01-17 | Closed | Cosmetic | 18

## Test cases modified Today (hidden)
Test cases modified Today | Sum of COUNT(*)
Passed | 6
(blank)
Grand Total | 6 | Status | Count | Date | Executed TC
|  | No run |  | 2014-01-14 | 0 | Row Labels | Sum of Executed TC
|  | N/A | 5 | 2014-01-15 | 24 | 2014-01-14 | 0
|  | Not completed | 7 | 2014-01-16 | 15 | 2014-01-15 | 24
|  | Failed | 15 | 2014-01-17 | 25 | 2014-01-16 | 15
|  | Passed | 24 | 2014-01-18 | 16 | 2014-01-17 | 25
|  | Blocked |  | 2014-01-19 | 5 | 2014-01-18 | 16
[6 empty] | 2014-01-19 | 5
[6 empty] | Grand Total | 85

## Management summary
Project: | Name of Project
Test manager:
Report generated by:
Summary:
Issues:
Hightlights:
Daily reports: |  | Updated | Weekly reports: |  | Updated
| D-Plan vs real | 2014-01-30 |  | W-Test shedule | 2014-01-30
| D-TC changes per day | 2014-01-30 |  | W-Test semafor | 2014-01-30
| D-Test environment | 2014-01-30 |  | W-TC per elements | 2014-01-30
| D-Progress of defects | 2014-01-30 |  | W-Defects per elements | 2014-01-30
| D- Defects changes per day | 2014-01-30 |  | W-Defects over SLA | 2014-01-30
| List of defects | 2014-01-30 |  | W- Number of open defects | 2014-01-30
|  |  |  | W-AVG time of open defects | 2014-01-30
-
-
-
-
-
-
-
-
-
-
-

## D-Plan vs real
Overal progress status in comparison to plan & overal Status Pies state & Success rate
| Description | [5 empty] | High problems
| Working day | 2014-01-09 | 2014-01-10 | 2014-01-11 | 2014-01-12 | 2014-01-13 | 2014-01-14 | 2014-01-15 | 2014-01-16 | 2014-01-17 | 2014-01-18 | 2014-01-19 | 2014-01-20 | 2014-01-21 | 2014-01-22 | 2014-01-23 | 2014-01-24 | 2014-01-25 | 2014-01-26 | 2014-01-27 | 2014-01-28 | 2014-01-29 | 2014-01-30 | 2014-01-31 | 2014-02-01 | 2014-02-02 | 2014-02-03 | 2014-02-04 | 2014-02-05
| Overal plan | 0 | 10 | 20 | 20 | 35 | 50 | 65 | 80 | 95 | 95 | 95 | 110 | 120 | 130 | 140 | 150 | 150 | 150 | 160 | 170 | 180 | 190 | 200 | 200
| Final Passed TCs - actual | 2014-01-09: 0; 2014-01-10: 13; 2014-01-11: 15; 2014-01-12: 15; 2014-01-13: 15; 2014-01-14: 24
| 1 Round execution result (Passed/Failed/N-A/Not Completed) | 2014-01-09: 0; 2014-01-10: 17; 2014-01-11: 24; 2014-01-12: 24; 2014-01-13: 24; 2014-01-14: 60
| Daily progres (Passed/Failed/N-A) | 2014-01-09: 0; 2014-01-10: 15; 2014-01-11: 21; 2014-01-12: 21; 2014-01-13: 21; 2014-01-14: 50
| GAP between plan and Reality | 2014-01-09: 0; 2014-01-10: -3; 2014-01-11: 5; 2014-01-12: 5; 2014-01-13: 20; 2014-01-14: 26
| Execution Status of TCs /Test Steps | 2014-01-09: Count TCs; 2014-01-10: %; 2014-01-11: Count Steps; 2014-01-12: %
| Passed | 2014-01-09: 24; 2014-01-10: 12; 2014-01-11: 211; 2014-01-12: 22
| Failed | 2014-01-09: 20; 2014-01-10: 10; 2014-01-11: 34; 2014-01-12: 4
| Not Completed | 2014-01-09: 6; 2014-01-10: 3; 2014-01-11: 12; 2014-01-12: 1
| Not Aplicable | 2014-01-09: 10; 2014-01-10: 5; 2014-01-11: 41; 2014-01-12: 4
| No Run | 2014-01-09: 140; 2014-01-10: 70; 2014-01-11: 643; 2014-01-12: 68
| Blocked | 2014-01-09: 0; 2014-01-10: 0; 2014-01-11: 0; 2014-01-12: 0
|  | 200 | 100 | 941 | 100
Quality rate - TC view
55%
Quality rate - TS view
86%
Quality rate: the percentage of executed tests / steps that ended in a Passed status compare to all of performed tests / STEP (declares the quality of the supplied code)
Is text execution going as was planned, or not.? I
f not, isproblem in number of test team stuf or in quality of delivery or both (problem in environment?).
-
-
-

## D-TC changes per day
Test case execution progress - changes in last period & changes per periode from start
Description
| Row Labels | Sum of Count
| Failed | 15
| N/A | 5
| Not completed | 7
| Passed | 24
| Grand Total | 51
Number of TC executed in last period per status. Is there progess in TC execution

## D-Test enviroment
Test environment availabitity
| Workind Day = 1 MD [8 working hours] 9:00 - 17:00 1/2 hour = 6%, 1 hour = 13%... | [24 empty] | Overall availability | Actual week 15 | week 14 | week 13
Date | Description of problem, Responsible | 8:30 | 9:00 | 9:30 | 10:00 | 10:30 | 11:00 | 11:30 | 12:00 | 12:30 | 13:00 | 13:30 | 14:00 | 14:30 | 15:00 | 15:30 | 16:00 | 16:30 | 17:00 | 17:30 | Unavailability in hours | Unavailability in % | Number of not Passed TC | Number of blocked TC | Blocked TC in % | 66.41% | 57.58% | 68.92% | 73.79% | 8:00
2013-10-04 | patch window | 8:30 | 9:13 | [17 empty] | 0:12 | 2.5% | 1540 | 1540 | 100%
2013-10-04 | prolongation of patch window due problems |  |  | 9:25 | 10:10 | [15 empty] | 0:45 | 9.375% | 1540 | 180 | 11.69%
2013-10-04 | deployment of hot fixies | [5 empty] | 10:55 | 11:54 | [12 empty] | 0:56 | 11.67% | 1525 | 92 | 6.033%
2013-10-04 | Unavailability of CRM | [8 empty] | 12:50 |  |  | 14:00 | [7 empty] | 2:07 | 26.46% | 1505 | 27 | 1.794%
2013-10-04 | patch window | [11 empty] | 14:00 |  | 14:53 | [5 empty] | 0:53 | 11.04% | 1505 | 0 | 0%
| Sum for 4/10/2013 | [19 empty] | 4:53 | 61.04% |  |  | 23.9% | 42.47%
2013-10-07 | nasadzovacie okno | 8:30 | 9:02
2013-10-07 | od polnoci sa nam nespracuvavaju requesty na pin61 - intreuro wM nejdi preto lebo im nebezi repository databaza…;a ta nebezi preto lebo niekto rebootol DB server…;no a DBA to nemozu nastartovat lebo nemaju disky restore RMCA klienta - hesla Skrovan, Lajstrik | 7:38 | [10 empty] | 13:57 | [7 empty] | 1:30
2013-10-07 | nasadzovacie okno | [11 empty] | 14:00 | 14:37
2013-10-07 | Rozkompilovane prostredie nefunkcne FE Activnet Chyba! • Nie je možné zapísať dáta do databázy (main) ORA-06508: PL/SQL: could not find program unit being called Villim: Rollbackoval som balik KURIER.API_KURIER a to rozbilo dalsie veci | [12 empty] | 14:30 |  | 15:30
| Sum for 7/10/2013 | [19 empty] | 1:30 | 18.75%
2013-10-08 | nasadzovacie okno | 8:30 | 9:16 | [15 empty] | 0:16 | 8:00 | 6:56
2013-10-08 | nasadzovacie okno | [11 empty] | 14:00 |  | 14:48 |  |  |  | 0:48
| Sum for 8/10/2013 | [19 empty] | 6:56 | 86.67%
2013-10-09 | nasadzovacie okno | 8:30 | 9:15 | [15 empty] | 0:15 |  | 6:52
2013-10-09 | nasadzovacie okno | [11 empty] | 14:00 | 14:37 |  |  |  |  | 0:37
2013-10-09 | Rozkompilovany balik AN2.API_ACTION Na INTREURO sa mi pri novom subscriberovi Villim : Balik som prekompiloval a restartol prostredie | [16 empty] | 16:25 | 16:41 | 0:16
| Sum for 9/10/2013 | [19 empty] | 6:52 | 85.83%
2013-10-10 | nasadzovacie okno | 8:30 | 9:16 | [15 empty] | 0:16 |  | 6:58
| nasadzovacie okno | [11 empty] | 14:00 |  | 14:46 |  |  |  | 0:46
| Sum for 10/10/2013 | [19 empty] | 6:58 | 87.08%
2013-10-11 | nasadzovacie okno | 8:30 | 9:03 | [15 empty] | 0:03 |  | 7:15
| Patchovanie billingu | [7 empty] | 12:00 | [5 empty] | 15:08
| nasadzovacie okno | [11 empty] | 14:00 | 14:42 |  |  |  |  | 0:42
| Sum for 11/10/2013 | [19 empty] | 7:15 | 90.62%
2013-10-14 | nasadzovacie okno | 8:30 | 9:10
| [Testovanie] nezobrazuju sa nam pre MIPC moduly – predajne/predajcovia a neda sa robit zmeny v MIPC riesene s Villimom joby z obidvoch prostedi (intrEURO aj intrNB) zapisuju javasrcripty do rovnakeho adresara a tak moze dojst k prepisaniu. Podla info od Z. Blazicka by to tak malo byt nastavene iba na jednom prostredi. |  | 9:00
| [Priprava Test Dat] Vyskladnovaci Job nespracuva zasielky, stale vracia neuspesne volanie vyskladnenia poslane na Milana Zipaja AN2. pkg_jobs.p_vyskladnenie |  | 9:00 | [15 empty] | 17:02
| nasadzovacie okno | [11 empty] | 14:00 |  | 14:49
| [Priprava Test Dat] vytvorenie zasielky v CWH Po vypisani IMEI zariadenia , zadani adresy na dorucenie zasielky a kliknuti samostatneho buttonu "vytvor novu zasielku" vyhodi chybovu hlasku "zasielku nebola uspesne vytvorena" Toto pred poslednym nasadzovacim oknom bolo v poriadku. | [14 empty] | 15:20 | 16:00 |  |  |  | 0:00
| Portacia - white screen ORA-06531: Reference to uninitialized collection ORA-06512: at "AN2.PCK_QN_CORE38", line 2468 ORA-06512: at "AN2.PCK_QN_CORE38", line 6220 ORA-06512: at line 27 DAD name: web PROCEDURE : !an2.pck_qn_core38.p_do URL : http://test.intranet.orange.sk:80/pls/web/!an2.pck_qn_core38.p_do?xid=463214 [prekompilovanie nepomohlo - poslane na developera] | [17 empty] | 16:49
| Sum for 14/10/2013 | [19 empty] | 0:00 | 0%
2013-10-15 | nasadzovacie okno | 8:30 |  | 9:19 | [14 empty] | 0:19 |  | 6:58
| nasadzovacie okno | [11 empty] | 14:00 | 14:43 |  |  |  |  | 0:43
| Sum for 15/10/2013 | [19 empty] | 6:58 | 87.08%
2013-10-16 | nasadzovacie okno | 8:30 |  | 9:30 | [14 empty] | 0:30 |  | 6:59
| nasadzovacie okno | [11 empty] | 14:00 | 14:31 |  |  |  |  | 0:31
| Sum for 16/10/2013 | [19 empty] | 6:59 | 87.29%
2013-10-17 | nasadzovacie okno | 8:30 | 9:16 | [15 empty] | 0:16 |  | 6:53
| nasadzovacie okno | [11 empty] | 14:00 |  | 14:51 |  |  |  | 0:51
| Sum for 17/10/2013 | [19 empty] | 6:53 | 86.04%
2013-10-18 | nasadzovacie okno | 8:30 | 9:33 | [15 empty] | 0:33 |  | 6:44
| nasadzovacie okno | [11 empty] | 14:00 | 14:43 |  |  |  |  | 0:43
| Sum for 18/10/2013 | [19 empty] | 6:44 | 84.17%
2013-10-21 | nasadzovacie okno | 8:30 |  | 9:20 | [14 empty] | 3:03
| problemy v Aktis, AN (obe prostredia) V Aktise sa nam pre CN s aktivnymi MIPC GSM/SIP tato skutocnost nezobrazuje, ani nas nepusti do modulu. Vyhlasi nam ze sluzba na CN nie je aktivna. V AN sa nezobrazuje mipc cast pre N_NORMA s VPN pausalom. Chybu sposobil Druska Pavel <pavel.druska@isdd.sk> v selfcare nespravnym parametrom | [8 empty] | 12:23 |  |  | 14:10 | [5 empty] | 2:29 |  | 5:32
| nasadzovacie okno | [11 empty] | 14:00 | 14:31
| Sum for 21/10/2013 | [19 empty] | 5:32 | 69.17%
2013-10-22 | nasadzovacie okno | 8:30 | 9:05
| nasadzovacie okno | [11 empty] | 14:00 | 14:35 | [6 empty] | 7:20
| Sum for 22/10/2013 | [19 empty] | 7:20 | 91.67%
2013-10-23 | nasadzovacie okno | 8:30 | 9:09 | [17 empty] | 1:33
| rozkompilovany balik padaju vsetky MIPC requesty na chybe: ERROR: ORA-06508: PL/SQL: could not find program unit being called pre PKG_MIPC_API.f_modify_CALL_TRANSFER_enq Poslany mail na prekompilovanie balika mipc.pkg_api_xml na INTREURO (Vladka Kleinova) |  |  |  |  | 10:42 | [6 empty] | 14:00 | [7 empty] | 2:19
| nasadzovacie okno | [11 empty] | 14:00 | 14:41
| Sum for 23/10/2013 | [19 empty] | 2:19 | 28.96%
2013-10-24 | nasadzovacie okno | 8:30 | 9:13 | [17 empty] | 3:08
| chyba vo Flexe - RIS ORA-01403: no data found ORA-06512: at "AN2.PCK_RIS_UTILS_WS", line 2862 ORA-06512: at "AN2.PCK_RIS_UTILS_WS", line 3578 ORA-06512: at "AN2.PCK_RIS_UTILS_WS", line 3207 ORA-06512: at line 27 | [8 empty] | 12:21 |  |  | 13:49
| Padli nam aplikace na intrNB aj intrEure Internet Explorer cannot display the webpage aj na produkcii | [10 empty] | 13:45
| nasadzovacie okno | [11 empty] | 14:00 | 14:32
| Sum for 24/10/2013 | [19 empty] | 3:08 | 39.17%
| nasadzovacie okno | 8:30 | 9:17 | [17 empty] | 4:43
| nasadzovacie okno | [11 empty] | 14:00 |  | 14:47
| Nedostupna SIM cast MIPC zmluv v AN Internet Explorer cannot display the webpage potvrdzujem problem bol v Java komponente ale bol technologickeho charakteru, kde sa startoval cache modul v nespravnej verzii.(Roman Cicvak, Martin Stevanak) | [13 empty] | 15:09 |  |  |  |  | 17:49
| Sum for 25/10/2013 | [19 empty] | 4:43 | 58.96%

## D-Progress of Defects
Progress of Defects – All & top 10 defects
Description
| Number of all: |  | 52 |  |  | ALL | New | Open | Fixed | Ready to test | Rejected | Reopen | Closed
| Number of Open: |  | 0
| Number of Closed: |  | 52
| Number of Critical: |  | 3
[6 empty] | 2014-02-24 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[6 empty] | 2014-02-25 | 10 | 2 | 4 | 4 | 3 | 2 | 2
[6 empty] | 2014-02-26 | 2 | 4 | 2 | 1 | 1 | 4 | 7
[6 empty] | 2014-02-27 | 1 | 2 | 2 | 0 | 8 | 7 | 12
[6 empty] | 2014-02-28 | 2 | 5 | 8 | 8 | 7 | 7 | 18
[6 empty] | 2014-03-01 | 7 | 8 | 7 | 3 | 7 | 1 | 24
[6 empty] | 2014-03-02 | 7 | 7 | 8 | 8 | 9 | 9 | 29
[6 empty] | 2014-03-03 | 4 | 5 | 8 | 8 | 7 | 7 | 35
| Top 10 defects |  |  |  |  | 2014-03-04 | 4 | 6 | 8 | 9 | 9 | 9 | 38
| Defect ID | Severity | Responsible | Comment | Summary | 2014-03-05 | 10 | 5 | 8 | 8 | 8 | 9 | 39
| 23 | Major | Vendor 1 | [9 empty] | 52
| 18 | Major | Vendor 2
| 27 | Critical | Vendor 2
| 16 | Major | Vendor 3
| 11 | Major | Vendor 1
| 15 | Major | Vendor 2
| 52 | Major | Vendor 2
Status of All defects per time period.
Top 10 defects to resolve.

## D-Defects changes per day
Defects changes in last period & changes per day from start
Description
| Count of Status | Severity
| Status | Cosmetic | Critical | Major | Minor | Grand Total
| Closed |  | 1 |  | 1 | 2
| Fixed |  |  |  | 1 | 1
| New | 1 |  | 2 |  | 3
| Open | 1 | 2 |  |  | 3
| Ready to test |  |  | 1 |  | 1
| Rejected |  |  | 1 | 1 | 2
| Grand Total | 2 | 3 | 4 | 3 | 12
Update of defect status per time period

## W-Test shedule
Test schedule
Test cycle | Feb |  |  | Mar |  |  |  | Apr |  |  |  | May |  |  |  | Jun |  |  |  |  | Jul
| 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31
Element A | Round 1
Element B | Round 1
Element C | Round 1
Element 1 | [17 empty] | Round 3
Element 2 | [9 empty] | Round 2
Element 3 | Round 1
Element 4
Element 5 |  | Round 1 | [15 empty] | Round 3
CRM for A1 | Round 1 | [8 empty] | Round 2
CRM for A2 | [9 empty] | Round 2
CRM for A3 | [9 empty] | Round2

## W-Test semafor
Test cycle status - semafor report
Description
| Test element | Test cycle | Round | Progress | Tests completed (%) | Time consumed (%) | Test start date | Test end date | Days to deadline | Project status | Total Testcases | No Run TC | Passed TC | Failed TC | N/A TC
| Element 1 | A | Round 1 | 0.875 | 87.5% |  | 2014-01-14 | 2014-03-26 | 946 | -12.5% | 400 | 22 | 350 | 10 | 5
|  | B | Round 1 | 0.54545 | 54.55% |  | 2014-02-24 | 2014-03-26 | 946 | -45.45% | 220 | 33 | 120 | 4 | 2
|  | C | Round 1 | 0.45902 | 45.9% |  | 2014-02-25 | 2014-03-30 | 942 | -54.1% | 122 | 21 | 56 | 6 | 3
|  | D | Round 1 | 0.36052 | 36.05% |  | 2014-02-26 | 2014-03-30 | 942 | -63.95% | 233 | 58 | 84 | 3 | 10
| Element 2 | E | Round 1 | 0.75 | 75% |  | 2014-02-28 | 2014-04-19 | 922 | -25% | 200 | 20 | 150 | 2 | 2
|  | F | Round 2 | 0.66667 | 66.67% |  | 2014-03-01 | 2014-04-20 | 921 | -33.33% | 333 | 10 | 222 | 3 | 1
|  | G | Round 2 | 0.56561 | 56.56% |  | 2014-03-02 | 2014-04-21 | 920 | -43.44% | 221 | 11 | 125 | 2 | 3
|  | H | Round 2 | 0.75 | 75% |  | 2014-03-03 | 2014-04-22 | 919 | -25% | 244 | 113 | 183 | 2 | 7
|  | I | Round 2 | 0.91408 | 91.41% |  | 2014-03-04 | 2014-04-23 | 918 | -8.592% | 547 | 10 | 500 | 3 | 7
| Element 3 | J
K
L
M
N
Formulas:
Days to deadline = (TODAY())-[Test end date]
-

## W-TC per elements
Overall view of TC per elements
Description
| Element | Failed | N/A | No Run | Not Completed | Passed | Grand Total
| Element1 | 96 | 72 | 67 | 78 | 66 | 379
| Element2 | 2 | 53 | 60 | 76 | 99 | 290
| Element3 | 73 | 54 | 86 | 94 | 54 | 361
| Element4 | 51 | 93 | 63 | 100 | 78 | 385
| Element5 | 81 | 98 | 71 | 72 | 69 | 391
| Element6 | 87 | 88 | 88 | 68 | 90 | 421
| Element7 | 79 | 89 | 95 | 93 | 65 | 421
Element view
Element1
| Status | Count | %
| Failed | 96 | 25.33%
| N/A | 72 | 19%
| No Run | 67 | 17.68%
| Not Completed | 78 | 20.58%
| Passed | 66 | 17.41%
| Grand Total | 379 | 100%
Element2
| Status | Count | %
| Failed | 2 | 0.6897%
| N/A | 53 | 18.28%
| No Run | 60 | 20.69%
| Not Completed | 76 | 26.21%
| Passed | 99 | 34.14%
| Grand Total | 290 | 100%
Element3
| Status | Count | %
| Failed | 73 | 20.22%
| N/A | 54 | 14.96%
| No Run | 86 | 23.82%
| Not Completed | 94 | 26.04%
| Passed | 54 | 14.96%
| Grand Total | 361 | 100%
Element4
| Status | Count | %
| Failed | 51 | 13.25%
| N/A | 93 | 24.16%
| No Run | 63 | 16.36%
| Not Completed | 100 | 25.97%
| Passed | 78 | 20.26%
| Grand Total | 385 | 100%
Element5
| Status | Count | %
| Failed | 81 | 20.72%
| N/A | 98 | 25.06%
| No Run | 71 | 18.16%
| Not Completed | 72 | 18.41%
| Passed | 69 | 17.65%
| Grand Total | 391 | 100%
Element6
| Status | Count | %
| Failed | 87 | 20.67%
| N/A | 88 | 20.9%
| No Run | 88 | 20.9%
| Not Completed | 68 | 16.15%
| Passed | 90 | 21.38%
| Grand Total | 421 | 100%
Element7
| Status | Count | %
| Failed | 79 | 18.76%
| N/A | 89 | 21.14%
| No Run | 95 | 22.57%
| Not Completed | 93 | 22.09%
| Passed | 65 | 15.44%
| Grand Total | 421 | 100%
If is there problem with TC execution, in whitch element?

## W-Defects per elements
Open defects - Status per period
| Description | [8 empty] | Hight problems
| Element | New | Open | Fixed | Ready to test | Rejected | Reopen | Closed | Grand Total
| Element1 | 70 | 87 | 64 | 87 | 75 | 75 | 74 | 383
| Element2 | 75 | 78 | 94 | 78 | 77 | 84 | 55 | 402
| Element3 | 92 | 60 | 84 | 72 | 98 | 68 | 89 | 406
| Element4 | 90 | 94 | 92 | 80 | 90 | 62 | 91 | 446
| Element5 | 58 | 71 | 65 | 72 | 51 | 90 | 58 | 317 |  |  |  | New | Open | Fixed | Ready to test | Rejected | Reopen | Closed
| Element6 | 76 | 92 | 97 | 82 | 62 | 78 | 87 | 409 |  |  | 2014-02-21 | 10 | 2 | 2 | 3 | 1 | 1 | 1
| Element7 | 80 | 66 | 92 | 77 | 94 | 75 | 53 | 409 |  |  | 2014-02-22 | 11 | 3 | 2 | 2 | 0 | 2 | 2
[12 empty] | 2014-02-23 | 10 | 5 | 3 | 2 | 0 | 0 | 5
[12 empty] | 2014-02-24 | 10 | 6 | 5 | 3 | 1 | 2 | 9
| Defects by status for each element in time | [10 empty] | 2014-02-25 | 9 | 5 | 2 | 2 | 2 | 8 | 10
[12 empty] | 2014-02-26 | 9 | 4 | 3 | 2 | 0 | 2 | 12
| Element1 | [9 empty] | Element2 | 2014-02-27 | 8 | 5 | 2 | 3 | 2 | 3 | 14
[12 empty] | 2014-02-28 | 9 | 4 | 2 | 2 | 0 | 2 | 16
[12 empty] | 2014-03-01 | 8 | 6 | 3 | 3 | 0 | 1 | 18
[12 empty] | 2014-03-02 | 7 | 5 | 2 | 1 | 2 | 1 | 25
| Element3 | [9 empty] | Element4
| Element5 | [9 empty] | Element6
Element7
- number of defects per status per element
- progres of defects per status per element in time period
- is there problem in defect execution? In which element?
-
-

## W-Defects over SLA
Defects over SLA
Description
| Vendor 1 | TTA |  | TTS |  | SLA metric | Vendor 2 | First answer |  | Final answer |  | Path delivery |  | SLA metric
| G0-Critical |  | 1 |  | 4 | 4 h / 2 d | G0-Critical |  | 5 |  | 1 |  | 1 | 2 d / 5 d /8 d | 1 | 4
|  |  | of |  | of |  |  |  | of |  | of |  | of |  | 19 | 6
|  |  | 20 |  | 10 |  |  |  | 20 |  | 10 |  | 10
| G1-Major |  | 2 |  | 1 | 1 d / 5 d | G1-Major |  | 1 |  | 2 |  | 1 | 10 d / 20 d / Clean release | 2 | 1
|  |  | of |  | of |  |  |  | of |  | of |  | of |  | 8 | 9
|  |  | 10 |  | 10 |  |  |  | 10 |  | 10 |  | 10
| G2-Minor |  | 10 |  | 1 | 1 d / 10 d | G2-Minor |  | 2 |  | 1 |  | 1 | 20 d / 40 d / Next release | 10 | 1
|  |  | of |  | of |  |  |  | of |  | of |  | of |  | 30 | 7
|  |  | 40 |  | 8 |  |  |  | 40 |  | 8 |  | 8
| G3-Cosmetic |  | 5 |  | 1 | 3 d / 20 d | G3-Cosmetic |  | 2 |  | 1 |  | 1 | 30 d / Clean release / Roadmap | 5 | 1
|  |  | of |  | of |  |  |  | of |  | of |  | of |  | 6 | 29
|  |  | 11 |  | 30 |  |  |  | 11 |  | 11 |  | 11
| Vendor 3 | Response Time |  | Fix Time |  | SLA metric | Vendor 4 | Acknowledgement or Guaranteed response time |  | Guranteed Service restore time |  | SLA metric
| G0-Critical |  | 1 |  | 1 | 2 h / 2 d | G0-Critical |  | 2 |  | 5 | 30 m / 4 h
|  |  | of |  | of |  |  |  | of |  | of
|  |  | 20 |  | 10 |  |  |  | 20 |  | 40
| G1-Major |  | 1 |  | 1 | 24 h / 24 d | G1-Major |  | 1 |  | 6 | 1 h / 8 h
|  |  | of |  | of |  |  |  | of |  | of
|  |  | 10 |  | 10 |  |  |  | 10 |  | 30
| G2-Minor |  | 1 |  | 1 | 48 h / 30 d | G2-Minor G3-Cosmetic |  | 10 |  | 1 | 4 h / 48 h
|  |  | of |  | of |  |  |  | of |  | of
|  |  | 40 |  | 8 |  |  |  | 40 |  | 20
| G3-Cosmetic |  | 1 |  | 1 | 48 h / 30 d
|  |  | of |  | of
|  |  | 11 |  | 11
10
20
Is there any problem with SLA ?

## W- Number of open defects
OPEN defects
Description
|  |  | FT | Test team | Supplier | OSK
|  | Open | 10 |  | 4 | 2
|  | New | 1 |  | 2 | 1
|  | Reopen | 2 |  | 3 | 11
|  | Rejected |  | 2
|  | Ready to test |  | 10
|  |  | antalp | x_marin | x_drobny | x_marecek | x_bohunicky | kaufmann | jambrich | x_volar | x_pis
|  | Open | 2 | 3 | 2 |  |  | 2 | 1
|  | New | 1 | 1 | 2 |  |  | 3 | 2
|  | Reopen | 1 | 4 | 2 |  |  | 1 | 3
|  | Rejected |  |  |  | 2 | 1 |  |  | 3 | 1
|  | Ready to test |  |  |  | 3 | 4 |  |  | 1 | 4
|  |  | P.Minarikova | J.Strmiska | M.Kovar | A.Kovacicova | L. Duk | D.Ziska | M.Kovac | A.Smutny | R.Zaprazny
|  | Open | 2 | 3 | 2 |  |  | 2 | 1
|  | New | 1 | 1 | 2 | 2 | 8 | 3 | 2 |  | 5
|  | Reopen | 1 | 4 | 2 |  |  | 1 | 3 | 2
|  | Rejected |  |  |  | 4 | 2 | 2 |  | 3 | 1
|  | Ready to test | 3 | 2 |  | 2 | 3 |  | 2 | 1 | 4
Open defects - New, Open, Reopen, Fixed, Rejected, Ready to test
Number of defects per team, per responsible, per resolution engineer

## W-AVG time of open defects
Average resolution time of defects
Description
Menovky stĺpcov
Menovky riadkov | New | Celkový súčet
Huawei
Celkový súčet
Menovky stĺpcov
Menovky riadkov | New | Open | Celkový súčet
tester 1
tester 2
tester 4
tester 5
tester 6
Celkový súčet
Menovky stĺpcov
Menovky riadkov | Celkový súčet
Celkový súčet
Open defects - New, Open, Reopen, Fixed, Rejected, Ready to test
Average resolution time of defects per team, per responsible, per resolution engineer

## List of defects
Defect ID | Summary | Description | Comments | Detected By | Assigned To | Detected in Cycle | Detected in Release | Detected on Date | Modified | Priority | Severity | Status
1 | xxxxxxxxxxxxx | xxxxxxxxxxxxx | xxxxxxxxxxxxx | tester1 | tester2 | e1 | e1 | 2013-11-18 | 2014-01-13 09:35 |  | G3-Minor | Open
2 | xxxxxxxxxxxxx | xxxxxxxxxxxxx | ddddddddddddd | tester2 | tester2 | e1 | e1 | 2013-11-19 | 2014-01-13 09:35 |  | G3-Minor | Open
3 | xxxxxxxxxxxxx | xxxxxxxxxxxxx | aaaaaaaaaaaaa | tester2 | tester2 | e2 | e2 | 2013-11-19 | 2014-01-10 14:22 |  | G2-Medium | Closed
4 | xxxxxxxxxxxxx | xxxxxxxxxxxxx | aaaaaaaaaaaaa | tester1 | tester2 | e2 | e2 | 2013-11-19 | 2013-11-25 15:21 |  | G0-Critical | Closed
5 | xxxxxxxxxxxxx | xxxxxxxxxxxxx | aaaaaaaaaaaaa | tester2 | tester1 | e3 | e3 | 2013-11-19 | 2014-01-13 09:36 |  | G2-Medium | Open
6 | xxxxxxxxxxxxx | xxxxxxxxxxxxx | aaaaaaaaaaaaa | tester2 | tester1 | e3 | e3 | 2013-11-20 | 2014-01-13 09:36 | U3-Not urgent | G3-Minor | Open
7 | xxxxxxxxxxxxx | xxxxxxxxxxxxx | aaaaaaaaaaaaa | tester1 | tester1 | e3 | e3 | 2013-11-20 | 2014-01-10 14:28 | U2-Medium | G2-Medium | Closed
8 | xxxxxxxxxxxxx | xxxxxxxxxxxxx | aaaaaaaaaaaaa | tester1 | tester2 | e3 | e3 | 2013-11-20 | 2014-01-13 09:40 |  | G1-Major | Open
9 | xxxxxxxxxxxxx | xxxxxxxxxxxxx | aaaaaaaaaaaaa | tester1 | tester2 | e4 | e4 | 2013-11-20 | 2014-01-13 09:45 |  | G2-Medium | Open
10 | xxxxxxxxxxxxx | xxxxxxxxxxxxx | aaaaaaaaaaaaa | tester2 | tester2 | e4 | e4 | 2013-11-20 | 2014-01-13 09:45 | U2-Medium | G2-Medium | Open
11 | xxxxxxxxxxxxx | xxxxxxxxxxxxx | aaaaaaaaaaaaa | tester2 | tester2 | e1 | e1 | 2013-11-20 | 2014-01-10 14:42 | U3-Not urgent | G3-Minor | Closed
12 | xxxxxxxxxxxxx | xxxxxxxxxxxxx | aaaaaaaaaaaaa | tester1 | tester2 | e2 | e2 | 2013-11-20 | 2014-01-13 09:46 |  | G3-Minor | Open
13 | xxxxxxxxxxxxx | xxxxxxxxxxxxx | aaaaaaaaaaaaa | tester1 | tester1 | e1 | e1 | 2013-11-20 | 2014-01-13 09:46 | U2-Medium | G2-Medium | Open
14 | xxxxxxxxxxxxx | xxxxxxxxxxxxx | aaaaaaaaaaaaa | tester2 | tester1 | e3 | e3 | 2013-11-20 | 2014-01-13 09:46 | U2-Medium | G2-Medium | Open

## List of defects 2 (hidden)
Defect ID | Assigned To | Detected in Cycle | Detected in Release | Detected on Date | Severity | Status | Number of days | Owner | Team